ASICS: AI-assisted assessment

Plan and timeline, October – December 2026 · for the ASICS program team and leadership

# 1. ASICS in brief

Janaagraha's Annual Survey of India's City-Systems (ASICS) assesses how well Indian cities are set up to deliver a good quality of life: their laws, institutions and processes. It covers verticals such as Parastatals, Urban Planning & Design (UPD) and mobility, and scores each city with the program team's expert methodology.

We are building an AI-assisted research tool that does the evidence work for each question. It finds the official sources, answers the question with a citation and quote, and drafts the score in the experts' scoring sheet for people to check. This lets ASICS cover more cities and verticals with evidence anyone can trace back to its source.

# 2. Where we are

- Pilot completed (end of September): Bengaluru, Parastatal vertical, with inputs from the program team.

- Phase 1 (now): turning the pilot into a structured project in LangGraph and Python, so the research runs as a set of AI agents working step by step with checks in between.

- API and costs: runs currently use Tech4Dev's API key. We will need Janaagraha's own key from mid-November, and will share cost estimates before then.

# 3. What we will demo on Tuesday 13 October

1–2 cities run end to end in the agentic setup, plus v1 of the scoring sheet structure requested by the program team:

- Step 1 · Find sources: the agent finds the city's parastatals, checks which websites are official, and builds a Citation Sheet of official sources. Every link is opened to confirm a person can read it, and a copy is saved. The team reviews and edits the sheet in Excel.

- Step 2 · Answer: each question is answered only from the reviewed Citation Sheet, naming the source and quoting it word for word; the quote is checked against the saved copy.

- Step 3 · Score (v1): answers go into the experts' scoring sheet. One sheet per vertical shows each question's AI score, the evidence behind it, and a highlighted column for the expert's own score. Scores add up from question to main question, agency, city and vertical, then the city's overall ASICS score.

- A simple app for the research team: choose verticals, cities and steps, follow progress, review in Excel. New verticals are added by configuration (Parastatal and UPD are set up), and the instructions given to the AI can be read and refined by the team.

# 4. The plan

- Phase 1 · to 30 October: accurate citations and answers for 1–2 cities (no AI scoring yet). The program team provides human answers and scores for 1–2 cities as the baseline, and we set up evals.

- Phase 2 · 2 – 20 November: evidence and answers correct for 12 cities, Parastatals first, then UPD and other verticals. This needs inputs from the program and tech teams to update and fine-tune the prompts.

- Phase 3 · 23 November – mid/end December: more cities, and AI scoring with outputs designed for human review.

- From now: a weekly review with the program and tech teams so we stay aligned.

# 5. How we will know it is accurate: evals

With the program team, we will build a set of human answers and scores for 1–2 cities and compare the AI's against them. This sets a baseline accuracy and becomes a test suite: every time we tune the prompts or change the AI model, we rerun it and see at once whether accuracy has gone up or down. The tool already records where people and the AI agree, question by question.

# 6. What we need from the program team

- Human answers and scores for 1–2 cities by 30 October (the eval baseline).

- The final question bank and scoring methodology for each vertical, so all three steps use the same version (by 23 October for Parastatals).

- Reviewers for the weekly review, and inputs to fine-tune prompts for each vertical.

- Janaagraha's API key by mid-November (with leadership), after the cost estimates.

# 7. Timeline at a glance

Weeks start on Mondays. To edit: change the dates in the table below and shade the week cells to match.

| Work | Dates | Sep | 5 Oct | 12 Oct | 19 Oct | 26 Oct | 2 Nov | 9 Nov | 16 Nov | 23 Nov | 30 Nov | 7 Dec | 14 Dec | 21 Dec | 28 Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Pilot | 1 Sep – 30 Sep |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 1 | 1 Oct – 30 Oct |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Demo: 1–2 cities end to end, agentic, with scoring sheet v1 | 13 Oct |  |  | ◆ |  |  |  |  |  |  |  |  |  |  |  |
| Citation and answer accuracy for 1–2 cities: review and tune prompts | 14 Oct – 30 Oct |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Human answers and scores for 1–2 cities (the baseline) | 14 Oct – 30 Oct |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Evals v1: compare AI with human answers, set the accuracy baseline and test suite | 19 Oct – 30 Oct |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 2 | 2 Nov – 20 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Evidence and answers correct for 12 cities: Parastatals | 2 Nov – 13 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| UPD and other verticals: Steps 1–3 for 12 cities | 9 Nov – 20 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cost estimates per city and vertical shared | 2 Nov – 13 Nov |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Switch from the Tech4Dev API key to Janaagraha's own key | 16 Nov |  |  |  |  |  |  |  | ◆ |  |  |  |  |  |  |
| Phase 3 | 23 Nov – 31 Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Expand to more cities | 23 Nov – 18 Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AI scoring with outputs designed for human review | 23 Nov – 18 Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Evals for AI scoring against human scores | 30 Nov – 18 Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ways of working | 12 Oct – 31 Dec |  |  | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● |

Pilot            Phase 1            Phase 2            Phase 3            Weekly review     ◆ milestone     ● weekly review

# 8. Work items (ready for Jira)

Columns map to Jira's CSV import fields: Issue Id, Issue Type, Summary, Parent Id, Team, Start date, Due date, Status, Depends on, Description. The same list is in ASICS_Timeline_Jira.csv next to this document.

| Issue Id | Type | Summary | Parent Id | Team | Start | Due | Status | Depends on | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ASICS-E0 | Epic | Pilot: Bengaluru (Parastatal) |  | Program + Tech | 1 Sep | 30 Sep | Done |  | Completed with inputs from the program team. |
| ASICS-0.1 | Story | Bengaluru pilot with program team inputs | ASICS-E0 | Program + Tech | 1 Sep | 30 Sep | Done |  |  |
| ASICS-E1 | Epic | Phase 1: agentic setup, 1–2 cities, accurate citations and answers |  | Tech + Program | 1 Oct | 30 Oct | In progress |  | No AI scoring in this phase: accuracy of citations and answers first. |
| ASICS-1.1 | Story | Structured project in LangGraph + Python: Steps 1–2 as agents (find sources → answer with citations) | ASICS-E1 | Tech | 1 Oct | 12 Oct | Done |  |  |
| ASICS-1.2 | Story | Scoring sheet structure v1, as requested by the program team (Step 3) | ASICS-E1 | Tech | 5 Oct | 12 Oct | Done |  |  |
| ASICS-1.3 | Milestone | Demo: 1–2 cities end to end, agentic, with scoring sheet v1 | ASICS-E1 | Tech + Program | 13 Oct | 13 Oct | Planned |  | Tuesday 13 October. |
| ASICS-1.4 | Story | Citation and answer accuracy for 1–2 cities: review and tune prompts | ASICS-E1 | Tech + Program | 14 Oct | 30 Oct | Planned | ASICS-1.3 |  |
| ASICS-1.5 | Story | Human answers and scores for 1–2 cities (the baseline) | ASICS-E1 | Program | 14 Oct | 30 Oct | Planned |  | Needed to measure the AI against. |
| ASICS-1.6 | Story | Confirm the final question bank and scoring methodology per vertical | ASICS-E1 | Program | 14 Oct | 23 Oct | Planned |  | Two versions of the Parastatal questions exist today; all steps must use one. |
| ASICS-1.7 | Story | Evals v1: compare AI with human answers, set the accuracy baseline and test suite | ASICS-E1 | Tech + Program | 19 Oct | 30 Oct | Planned | ASICS-1.5 |  |
| ASICS-E2 | Epic | Phase 2: 12 cities, Parastatals then UPD and other verticals |  | Tech + Program | 2 Nov | 20 Nov | Planned |  |  |
| ASICS-2.1 | Story | Evidence and answers correct for 12 cities: Parastatals | ASICS-E2 | Tech + Program | 2 Nov | 13 Nov | Planned | ASICS-1.4, ASICS-1.7 |  |
| ASICS-2.2 | Story | UPD and other verticals: Steps 1–3 for 12 cities | ASICS-E2 | Tech + Program | 9 Nov | 20 Nov | Planned | ASICS-1.6 |  |
| ASICS-2.3 | Story | Prompt fine-tuning with program team inputs; every change checked by evals | ASICS-E2 | Tech + Program | 2 Nov | 20 Nov | Planned | ASICS-1.7 |  |
| ASICS-2.4 | Story | Cost estimates per city and vertical shared | ASICS-E2 | Tech | 2 Nov | 13 Nov | Planned |  |  |
| ASICS-2.5 | Milestone | Switch from the Tech4Dev API key to Janaagraha's own key | ASICS-E2 | Janaagraha + Tech | 16 Nov | 16 Nov | Planned | ASICS-2.4 | From mid-November. |
| ASICS-E3 | Epic | Phase 3: more cities, AI scoring with outputs for human review |  | Tech + Program | 23 Nov | 31 Dec | Planned |  | Target mid-December; latest end of December. |
| ASICS-3.1 | Story | Expand to more cities | ASICS-E3 | Tech + Program | 23 Nov | 18 Dec | Planned | ASICS-2.1, ASICS-2.2 |  |
| ASICS-3.2 | Story | AI scoring with outputs designed for human review | ASICS-E3 | Tech + Program | 23 Nov | 18 Dec | Planned |  |  |
| ASICS-3.3 | Story | Evals for AI scoring against human scores | ASICS-E3 | Tech + Program | 30 Nov | 18 Dec | Planned | ASICS-3.2 |  |
| ASICS-3.4 | Story | Review, documentation and handover to the program team | ASICS-E3 | Tech + Program | 14 Dec | 31 Dec | Planned |  |  |
| ASICS-E4 | Epic | Ways of working: weekly program + tech review |  | Program + Tech | 12 Oct | 31 Dec | Planned |  | Every week from the demo onwards (day to be agreed). |